## Preview
View | This is a realese check list document which should be followed at the time of deployments
Contact Details | Name | Email - Id
IDP Mule BAU
Developer/Tester | Hemalata Yavarna | Hemalata.Yavarna@sa.gov.au
DBA | Asad Ali | Asad.Ali@sa.gov.au
Project Manager | Zac Anstee | Zac.Anstee@sa.gov.au
Reviewer | Steve Revill | Steven.Revill@sa.gov.au

## Pre-Deployment
SNo. | Task | Description | System -Env | Owner | Tester | DateTime | Status
1 | Deployment of Stored Proc "sp_GLBalances" and view [vw_GLTransactions] in CEDS Production | Deployment and Validation of SP & view accessibility via integration_user | CEDS - PROD - EDUGLD36 | Asad | Hema
4 | Validate CI/CD Pipeline for CEDS System API | CI/CD Pipeline Configuration for Prod | GitLab - Prod/Stg | Hemalata | IDP Mule BAU
5 | Validate CI/CD Pipeline for EMS System API | CI/CD Pipeline Configuration for Prod | GitLab - Prod/Stg | Hemalata | IDP Mule BAU
6 | Validate CI/CD Pipeline for MasterPiece System API | CI/CD Pipeline Configuration for Prod | GitLab - Prod/Stg | Hemalata | IDP Mule BAU
7 | Validate CI/CD Pipeline for Email Notification API | CI/CD Pipeline Configuration for Prod | GitLab - Prod/Stg | Hemalata | IDP Mule BAU
8 | Validate CI/CD Pipeline for Error API | CI/CD Pipeline Configuration for Prod | GitLab - Prod/Stg | Hemalata | IDP Mule BAU
9 | Validate CI/CD Pipeline for Finance Process API | CI/CD Pipeline Configuration for Prod | GitLab - Prod/Stg | Hemalata | IDP Mule BAU
10 | Validate CI/CD Pipeline for Board Expereince API | CI/CD Pipeline Configuration for Prod | GitLab - Prod/Stg | Hemalata | IDP Mule BAU
11 | Validate CI/CD Pipeline for Integration Master Data DB API | CI/CD Pipeline Configuration for Prod | GitLab - Prod/Stg | Hemalata | IDP Mule BAU
12 | Get your application CAB approved | TBC | TBC | TBC | TBC

## Deployment
SNo. | Task | Description | System -Env | Owner | Tester | DateTime | Status
1 | Deployment of CEDS System API | -Go to GitlLab Location: https://gitlab.idp.edudom02.sa.gov.au/d4e/idp/ict/ict-reform/ceds-database/ceds-db-system-api Code Version: Copy from Branch - "STG" -Click Deploy | IDP Prod | ICT Team | Hemalata/Steve
2 | Deployment of MasterPiece System API | Go to GitlLab Location : https://gitlab.idp.edudom02.sa.gov.au/d4e/idp/ict/ict-reform/masterpiece-database/masterpiece-db-system-api Code Version: Copy from Branch - "STG" Click Deploy | IDP Prod | ICT Team | Hemalata/Steve
3 | Deployment of EMS System API | Go to GitlLab Location : https://gitlab.idp.edudom02.sa.gov.au/d4e/idp/ict/ict-reform/ems-database/ems-db-system-api Code Version : Copy from Branch - "STG" Click Deploy | IDP Prod | ICT Team | Hemalata/Steve
4 | Deployment of Email Notification API | Go to GitlLab Location : https://gitlab.idp.edudom02.sa.gov.au/d4e/idp/ict/ict-reform/error-handling/email-gateway-system-api Code Version : Copy from Branch - "STG" Click Deploy | IDP Prod | ICT Team | Hemalata/Steve
5 | Deployment of Error API | Go to GitlLab Location : https://gitlab.idp.edudom02.sa.gov.au/d4e/idp/error/sys-error-api Code Version : Copy from Branch - "STG" Click Deploy | IDP Prod | ICT Team | Hemalata/Steve
6 | Deployment of Finance Process API | Go to GitlLab Location : https://gitlab.idp.edudom02.sa.gov.au/d4e/idp/ict/ict-reform/financial/financial-process-api Code Version : Copy from Branch - "STG" Click Deploy | IDP Prod | ICT Team | Hemalata/Steve
7 | Deployment of Board Experience API | Go to GitlLab Location : https://gitlab.idp.edudom02.sa.gov.au/d4e/idp/ict/ict-reform/board-system/board-experience-api Code Version : Copy from Branch - "STG" Click Deploy | IDP Prod | ICT Team | Hemalata/Steve
8 | Deployment of Integration Master Data DB API | Go to GitlLab Location : https://gitlab.idp.edudom02.sa.gov.au/d4e/idp/ict/ict-reform/integration-master-data/integration-master-data-db-system-api Code Version : Copy from Branch - "STG" Click Deploy | IDP Prod | ICT Team | Hemalata/Steve
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There is also a step for CAB approval which is required before deploying to Prod
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: owner is ICT team

## Post-Deployment
SNo. | Task | Description | System -Env | Owner | Tester | DateTime | Status
1 | Create a router for Board Experience API | Service Name : "board-experience-api-service-idp" Router Timeout : 5 mins | IDP-PROD | Hemalata
2 | Sanity Test | Using Postman hit a. Transactions endpoint b. Trail-balance endpoint | IDP-PROD | Hemalata
3 | Share Board Expereience API Credentials with Board Team | Username + Password needs to be shared via EMail/Ms Teams(TBD) |  | Hemalata | Board Team
4 | Share Sanity Test Results across for Successful Validation |  |  | Hemalata
5 | Board Team to do configuration in Board Application |  |  | Board Team | IDP BAU & Board Team
6 | Update Route timeout | kind: Route metadata: annotations: haproxy.router.openshift.io/timeout: 300s | IDP-PROD | Hemalata